## Sprint 26.06
Item # | Jira # | Category | Description | Env | Search Affected | Supplemental | Priority | Status | Workaround / Priority Justification | Reporter | New Searches OFF | Synchronization Issue? | Tested QA | Tested in STG | Dev Note | QA Note
1 |  | Fuzzy Search | Underscore operator is not working | QA1 | Regular Search | When searching by Document Attribute value = __d* it should return any attribute value where the letter 'd' is in 3rd position with any string after. | Low | ToDo | No workaround available | Diego J. |  |  | Working
2 |  | Regular / Custom Search | No results returned using All as Document Attribute Name and searching by value | Pineapple | Regular / Custom Search | Using All as Document Attribute Name and searching by value or partial value (%test%) Attribute Name: RegularRegressionSecond All: TestAutomationComplexValue All: %TestAutomation% → 1 document must be returned | High | Done |  | Diego F. |  |  | Not working | Not working |  | When searching for: All:%TestAutomation%. Two results are returned. One of them does not exist in the database — ES still shows stale document metadata.
3 |  | Attribute / Custom Search | Selecting only Attribute Value returns everything; selected value not shown in filters panel | Pineapple | Custom Search | Attribute value (location attribute) Everything returned. Value selected not displayed in filters panel. Assumption: selecting only "Attribute Value" should be treated as if "All" was selected as "Attribute Type". | High | Done |  | Diego F. |  |  | Working
4 |  | Projects | Documents within project are not included in generated Project Listing file | Encino | Project Search | When the Project Listing file is generated it only contains the header row; the documents are not included. | High | Done |  | Diego F. |  |  | Working | Listing file not created
5 |  | Search Results | Search results counter is not showing total results count once a filter is applied | QA1 | All |  | Low | Done |  | Diego J. |  |  | Working | Not working
6 |  | Search Results | Filtering in search results is not using sub-string exact match | QA1 | All |  | High | Open |  | Diego F. |  |  | Working | Not working
7 |  | Location Attribute Search | Search by location attributes is not returning results | Staging | Attribute Search | The following search does not return results: Attribute Type: Agreement # Attribute Value: 104180000 | High | Done |  | Diego J. |  |  |  | Working | Issue with Stg and Prod indexes — they were not set up correctly. Indexes are now fixed.