## Jan 2026 Most Updated
Item # | Jira # | Category | Description | Env | Search Affected | Supplemental | Priority | Status | Workaround / Priority Justification | Reporter | New Searches OFF | Synchronization Issue? | Tested QA | Tested PROD | Dev Note | Dev Fix
1 | 8875 | Search Results Grid | Error in results counter (results = -1) | QA1 | Attribute searches that should return zero |  | Medium | Done | No workaround available | Diego |  |  | passed |  |  | Fixed Indexing issue.
2 | 8875 | Search Results Grid | Document attribute Dates show like (2025-10-14T15:33:00.000Z) on Search Results | Merit | All |  | Medium | Done |  | Claire | [5 empty] | Changed to use date value on attributes instead of value for attribtues that store dates. Then converted from unix to date format isntead of showing iso format.
3 | 8875 | Search Results | Filename search is broken, it should be able to search for exact content.name value or fuzzy search with % signs | QA1 | All |  | High | Done |  | Claire |  |  | passed |  |  | A combination of case insensitifity and fuzzy searching . Meanign files were always being search fuzzily not exact even without the %.
4 | 8875 | Search Results | Document Attribute Value wildcards are not working (Invoice Number:aus%) (Invoice Number:%202O%) or Invoice Number:%2023% | QA1 | All |  | High | Done |  | Claire |  |  | passed |  |  | Added wilded card support for the mentioned search patterm.
5 | 8875 | Search Results | Linked documents do not show up in their linked locations nor with the "Linked From" check mark Ex. Document 182789 should be linked to (0Regression24.26-DELETE-2> Cab> test) | QA1 | All |  | High | Done |  | Claire |  |  | passed |  |  | Implemented linked from and linked to support on the api as well as fixed linked to and from logic in front end to show checkmarks when appropriate.
6 | 8875 | Search Results | Keywords:oilDepartment:AR-JACKSON Should pull back ~2589 documents but returns 0 | Merit | Regular |  | High | ToDo |  | Claire |  |  | not finished |  | This is a hard one still trying to figure it out.
7 | 8875 | Search Results Grid | Using the Search Results Keyword Filter does not work on the Document Type field. (Department:TX-HIDALGODocument Type:Well Log then type Well Log in search field) | Merit | All |  | Medium | Done |  | Claire |  |  | passed |  |  | Found and fix a case sensitivity issue while I dont know the exact outcome expected from this search. At the momebt the base search returns 43485 all docs on that dep that have that doc type then on top of that you apply a filter well log it will filter deaper using name and otehr attribtues resulting on a smaller list docs.
8 | 8875 | Search Results | Comment: Comment for Testing should pull back 1 record but instead pulls back 1123 | Merit | Attribute |  | Medium | Done |  | Claire |  |  | passed |  | Cant replicate when I search for the comment indicated I get 0 results but the db indicates no document has this comment and ES says the same. I was able to add a omment to a file and serach by said comment.
9 | 8875 | Search Results | County:INDEPENDENCE Folder:Land File should pull back ~1246 documents but returns 0 | Merit | Custom |  | High | Done |  | Claire |  |  | passed |  |  | This had a very complicated issue related to how we implmented search folders by name not by Id for custom search and how they tie to the general search of documents. Re implmented resolve to id from a folder name while not breaking the funcionality to resolve locations ids of folders that have some relations to there parents or grandparets based on one of ther locaiotns attribtues. Meanign if we search for a locaiton attribtue that is assigned to a cabinet then search for a folder under that cabinet all files on that folder are treated as if they have that locaiton attribute so. When we search by folder name we need to get all folder ids with that name but at the same time all folder ids with that name that are under a cabinet or a department that has the searched for locaiont attribute. Not even Claude helped me here RIP.
10 | 8875 | Performance | Databank Box:%Sub DocType:Agreement takes 29 seconds to return, on old search it only took 1-2 seconds | Merit | Custom |  | Medium | Done |  | Claire |  |  | passed but is not returning the right information as explained in the dev notes |  | This performance issue is an edge case if you do the exact same search but susing Agreements you will se is much faster and returns more resutls. Current theory after some investigation is that its becase elastic stored values for that document type in a very inconvinient way.
11 | 8875 | Search Results | Project Search is broken, "Search service returned no results or failed" | Merit | Project |  | High | Done |  | Claire |  |  | passed

## Bugs Old
Column1 | Item # | Jira # | Category | Recheck (1.8.26) | Description | Env | Search Affected | Supplemental | Priority | Status | Workaround / Priority Justification | Reporter | New Searches OFF | Synchronization Issue? | Tested PROD | Dev Note | Dev Fix
| 1 | DD-8486 | Search Results Grid | Done | Export to Excel Search Results only contain column headers, no data | QA1 | All - including project and tree |  | High | Done | No workaround available | Claire | Passed
| 2 |  | Performance | Done | Performance tests cannot be done until pagination is returning 10k or more results. (10k is acceptance critiera) | QA1 |  |  | High | Done |  | Claire
| 3 | DD-8430 | Document Action | Done | Using a Copied Link does not allow you to pull back the document, you get an error. "Requested content wasn't found." | QA1 | All - including project and tree |  | High | Done |  | Claire | Passed
| 4 | DD-8481 | Search Results | Done | Name column does not include content extension | QA1 | All - including project and tree |  | High | Done |  | Claire | Passed | -- |  | Missing extension on mapping
| 5 | DD-8481 | Document Previewer | Done | Document Previewer name does not include content extension | Z | All - including project and tree |  | High | Done |  | Claire | Passed |  |  | Missing extension on mapping
| 6 | DD-8481 | Document Action | Done | Replace is disabled | QA1 | All - including project and tree |  | High | Done |  | Claire | Passed |  |  | Missing functionality / user to document data is not supoerted in Webapp yet.
| 7 | DD-8481 | Document Action | Done | Upload New version is disabled | QA1 | All - including project and tree |  | High | Done |  | Claire | Passed |  |  | Missing functionality / user to document data is not supoerted in Webapp yet.
| 8 |  | Performance | Done | When scrolling through Attribute/Comment/Hashtag the search results columns are not loading quickly, they seem empty to the user (Example Location Attribute:THIRD VALUE) | QA1 |  | See Screenshot tab | High | Done |  | Claire | Passed
| 9 |  | Performance | Done | Entire screen is imperformant, the search is very slow, when scrolling, clicking on a document the previewer takes forever to load, etc. (Example Location Attribute:THIRD VALUE) | QA1 | Attribute/comment/hashtag (See if other QA members had issue on other search screens) | See Screenshot tab | High | Done |  | Claire | Passed
| 10 | Stream/On Hold | Document Upload | Done | When a file is uploaded and saved to a location, it cannot be found when the user searches for it. | PineappleAIGasCo |  |  | High | Done | Automated regression is failing due to this step | Diego S. | Passed
| 11 | DD-8430 | Document type | Done | Document type search is not filtering, is returning all the documents | QA1 | Regular + Attribute/comment/hashtag + Custom |  | High | Done |  | Valentina | Passed |  |  | This bug is caused by the webapp expecting a single value template id and the Webcore sending it as a list. | Change webapp to accept a list of template ids. Fileter based on that. After adjustments since we are changing how we filter based templates dues to sync perf issue Daniel Found one template change causes all docs to change.
| 12 | Stream/On Hold | Streaming Timing | Done | New Hashtag thats added is not searchable , "Claire". Search retruns 0 | QA1 | Attribute/comment/hashtag + Custom |  | High | Done |  | Claire | Passed
| 13 | DD-8481 | Created Date & last modified date | Done | This dates are being shown as 01/01/0001 for all the documents | QA1 | All - including project and tree | See Screenshot tab | High | Done |  | Valentina | Passed |  |  | Issues in mapping
| 14 | DD-8430 | Comment | Done | Comment "Claire" brings back 609811 results | QA1 | Attribute/comment/hashtag + Custom |  | High | Done |  | Claire | Passed (Brings back 3 results)
| 15 | DD-8487 | Search Results Grid | Done | Unable to filter documents in search results panel | QA1 | All - including project and tree |  | High | Done |  | Diego S. | Passed
| 16 | DD-8481 | Search | Done | Date attributes are not being corretly filtered |  | All |  | High | [6 empty] | Missing functionality / we did not consider difrent types of attributes specialy date from to or values from to.
| 17 | Stream/On Hold | Document Deleting | Done | When deleting a document, the search results are not refreshed, and some actions can be performed on the document. | PineappleAIGasCo | All - including project and tree |  | High | Done | Took 5 seconds and a refresh to be updated | Diego S. | Passed
| 18 | DD-8481 | Properties panel | Done | Unable to edit a document (location, document type, attributes) - The buttons are not displayed | PineappleAIGasCo | All - including project and tree |  | High | Done |  | Diego S. | Passed |  |  | Missing functionality / user to document data is not supoerted in Webapp yet.
| 19 | Stream/On Hold | Streaming | Done | Added Agreement # 176659000 location attribute to secondary location_id: 112538, 5 minutes ago and its not in elastic search yet | QA1 |  | GET 63_locations/_search { "query": { "term": { "location_id": "112538" } } } { "took" : 1, "timed_out" : false, "_shards" : { "total" : 1, "successful" : 1, "skipped" : 0, "failed" : 0 }, "hits" : { "total" : { "value" : 1, "relation" : "eq" }, "max_score" : 1.0, "hits" : [ { "_index" : "63_locations", "_type" : "_doc", "_id" : "112538", "_score" : 1.0, "_source" : { "location_id" : 112538, "location_type" : "cabinet", "name" : "176659000-GERALD E BURKE ET UX", "parent_id" : "457", "properties" : null, "system_id" : "63" } } ] } } | High |  |  | Claire
| 20 | DD-8430 | Location Attribute | Done | Searching by Agreement # 176659000 pulls back 609808, should pull back 7 (or 0 if value hasn’t made it to elastic yet) (Dont se it on this enviroment on elastic) Try | QA1 | Attribute/comment/hashtag |  | High | Done |  | Claire |  |  |  | We dont have the data on that envirome need to check why./ if you test a location attrtibute you know contains doucments the test will be targeted to search not sync
| 21 | DD-8488 | Search Results Grid | Done | Unable to sort documents in search results panel | QA1 | All - including project and tree |  | High | Done | Can sort by name, system doc, extented sort coming in another ticket | Claire
| 22 | DD-8481 | Document Action | Done | Every document thinks I have it "Checked Out" and has the document action "Check In" enabled | QA1 | All - including project and tree |  | High | Done | [5 empty] | Missing functionality / user to document data is not supoerted in Webapp yet.We dont have the user Id that has document locked in elastic.
| 23 | DD-8430 | Location Attribute | Done | County = Independence should pull back 9133 but its pulling back all docs in system State: TX on Merit | Merit | Attribute/comment/hashtag |  | High | Done |  | Claire |  |  |  | We dont have the data on that envirome need to check why.
| 24 | DD-8430 | Search | Done | Custom Search Databank Box: % should bring back more than 500k | Merit | Custom |  | High | Done |  | Claire |  |  |  | Wrong Elasticsearch operators/logic
| 25 | DD-8430 | Search | Done | Custom Search API12:030630000100Folder:Well File should pull back 303 but pulls back 8 | Merit | Custom |  | High | Done |  | Claire |  |  |  | Using match not term for keyword seaches
| 26 | DD-8430 | Location Attribute | Done | Unable search documents by location attribute (Offshore Platform 4:TEST ATTRIBUTE - DEP should return 10 documents but 610016 returned) | QA1 | Custom |  | High |  |  | Diego S. |  |  |  | Using match not term for keyword seaches
| 27 | DD-8430 | Document Attribute Search | Broken | Document Attribute Value wildcards are not working (Invoice Number:aus%) (Invoice Number:%202O%) or Invoice Number:%2023% | QA1 | Custom |  | High |  | Compared to Staging it should not be case sensitive | Diego S.
| 28 | DD-8430 | Document Attribute Search | Done | Searching by Folder - Not all documents returned when multiple folders have the same name (Folder: GulfStream Resources) | QA1 | Custom |  | High |  |  | Diego S. |  |  |  | Web App works with one single folder id not a list. When multiple folders have the same they have difrent ids. The webapp will hsow the contents of the folder selected
| 29 | DD-8430 | Search | Done | Search by document attributes is not returning any results | QA1 | All |  | High | Done |  | Diego J.
| 30 | DD-8482 | Performance impovements | Done | Implement pagination and integrate it with the front end (Webapp issue). | N/a | N/a |  | High | Done
| 31 | DD-8482 | Performance impovements | Done | Remove the duplicate Elastic request for count and integrate counting into the document request (Webapp issue). | N/a | N/a |  | High | Done
| 32 | DD-8484 | Performance impovements | Done | Implement caching for control access query building so we don’t make unnecessary database requests (Webapp control access issue). | N/a | N/a |  | High | Done
| 33 | DD-8485 | Performance impovements | Done | Optimize front-end integration so we only pull necessary data, tailoring responses to what the UI actually needs (Web Core integration issue). | N/a | N/a |  | High | Done
| 34 |  | Keyword Search | Done | Searching by multiple keyword search 'samurai operating' (OR Operator) is returning 6546 docs and must return 1 document. | QA1 |  |  | High |  |  | Diego J.
| 35 | [DD-8677] Dev Adjustment for Searches part 2 - Jira | Custom Search | Done | Folder: Well FIle should bring back all documents associated to a folder.name = "Well File" so more than 100k. | Merit |  |  | High |  |  | Claire
| 36 |  | Sort Order | Done | Sort Order should be by Last Modified Date | All |  |  | High |  |  | Claire
| 37 | DD-8678 | Document Attribute Search | Done | Filter by Document Attribute Filesize does not pull back any records | Merit |  | See Screenshot tab | High |  |  | Claire
| 38 |  | Location Attributes |  | Search by COUNTY = Independence (only some properties I see listed in elastic, not all location attributes are there.) | Merit |  | See Screenshot tab | High |  |  | Claire
| 39 |  | Document Attribute Search | Done | Search by Sub Doc Type = Agreement brings back both Sub Doc Type Agreement and Agreements, should be exact matches only | Merit |  |  | High |  | Long running query | Claire
| 40 |  | Document Attribute Search | Done | Document Type:InvoiceDocument Date:10/14/2025-10/14/2025 Pulls back files with many different document dates other than 10/14/2025 | Merit |  |  | High |  |  | Claire
Done | 41 | DD-8678 | Document Attribute Search | Done | Extension:.pdf pulls back 0 results | Merit |  |  | High |  |  | Claire | [5 empty] | Done
| 42 | DD-8678 | Document Attribute Search | Broken | Filename search is broken, it should be able to search for exact content.name value or fuzzy search with % signs | Merit |  |  | High |  |  | Claire
| 43 | DD-8678 | Document Attribute Search | Done | Created Date:Between Last - & 1 Months ¦ we need to be able to pull back the last months data (0-1 months in past) | Merit |  |  | High |  |  | Claire | [5 empty] | Done
| 44 | DD-8678 | Document Attribute Search | Done | Created Date:Between Last - & 1 Days ¦ we need to be able to pull back documents uploaded in the last 24 hours | Merit |  |  | High |  |  | Claire | [5 empty] | Done
| 45 |  | Hashtag | Done | HashTag:Olipop should return one document. This issue is not due to lack of data in elastic | Merit |  | See Screenshot tab | High |  |  | Claire | [5 empty] | Done
| 46 |  | Location Attributes |  | adeptest:DRPEPPER | Merit |  | See Screenshot tab | High |  |  | Claire
| 47 |  | Linked Documents | Broken | Linked documents do not show up in their linked locations nor with the "Linked From" check mark Ex. Document 182789 should be linked to (0Regression24.26-DELETE-2> Cab> test) | QA1 |  |  | High |  |  | Claire
| 48 |  | Document Attributes OR Operation
49
50
51
52
FIXED

## Sprint 26.05
Item # | Jira # | Category | Description | Env | Search Affected | Supplemental | Priority | Status | Workaround / Priority Justification | Reporter | New Searches OFF | Synchronization Issue? | Tested QA | Tested in STG | Dev Note | QA Note
1 |  | Fuzzy Search | Underscore operator is not working | QA1 | Regular Search | When searching by Document Attribute value = __d* it should return any attribute value where the letter 'd' is in 3rd position with any string after. | Low | ToDo | No workaround available | Diego J. |  |  | Working
2 |  | Regular/Custom search | No results returned using All as Document Attribute Name and searching by value | Pineapple | Regular/Custom search | Using All as Document Attribute Name and searching by value or partial value (%test%) Attribute Name: RegularRegressionSecond All:TestAutomationComplexValue All:%TestAutomation% 1 document must be returned | high | Done |  | Diego F. |  |  | Not working | Not working |  | When searching for: All:%TestAutomation%. Two results are returned. One of them does not exists in the database. ES still shows the document metadata.
3 |  | Attribute/Custom search | Selecting only attribute value it returns everything and the value selected is not displayed in filters panel | Pineapple | Custom search | Attribute value (location attribute) Everything returned. Value selected not displayed in filters panel We assume that selecting only "Attribute Value" must be treated as if "All" had been selected as "Attribute Type" | high | Done |  | Diego F. |  |  | Working
4 |  | Projects | Documents within project are not included in generated Project Listing file | Encino | hy | When the Project Listing file is generated, it only contains the header, the documents are not included | high | Done |  | Diego F. |  |  | Working | Listing file not created
5 |  | Search Results | Search results counter is not showing the total results count once a filter is applied | QA1 |  |  | low | Done |  | Diego J. |  |  | Working | Not working
6 |  | Search Results | Filtering in search results is not using sub strings exact match | QA1 |  |  | high |  |  | Diego F. |  |  | Working | Not working
7 |  | Location Attribute Search | Search by location attributes is not returning results | Staging |  | The following search does not return attributes: Attribute Type: Agreement # Attribute Value: 104180000 | high | Done |  | Diego J. |  |  |  | Working | We have an issue with Stg and Prod Indexes that if tested in stg and prod env it will not work. I need to look into why this happend Indexes were not set up correcly.
delete actions

## Sprint 26.06
Item # | Jira # | Category | Description | Env | Search Affected | Supplemental | Priority | Status | Workaround / Priority Justification | Reporter | New Searches OFF | Synchronization Issue? | Tested QA | Tested in STG | Dev Note | QA Note
1
2

## Screenshots
Issue #9 |  | Issue #13
Issue #10
Issue 37
Issue 38
Issue 46 | Issue 45